## Sheet1
Task Name | Amount of work in project 3 | Project 3 Productivity rate | project 3 duration | Amount of work in project 1 | Project 1 Productivity rate | Amount of work in project 2 | Project 2 Productivity rate
Project Plan
Write Plan | 76 pages | 2 pages/Hour | 4.75 | 169 pages | 2 pages/Hour | 117 pages | 2 pages/Hour
Review Plan
Preparation for review |  | 4.5 pages/Hour | 2.111 |  | 4 pages/Hour |  | 5 pages/Hour
Review Meeting |  | 7 pages/Hour | 1.357 |  | 6 pages/Hour |  | 8 pages/Hour
Rework | 24 defetcs | 5 defects/Hour | 0.6 | 32 defects | 5 defects/Hour | 51 defects | 5 defects/Hour
Documented Software Development Process Updates
Process Changes | 44 Changes | 5 Changes/Hour | 1.1
Review Changes
Preparation for review |  | 3 Changes/Hour | 1.833
Review Meeting |  | 5 Changes/Hour | 1.1
Rework | 11 defects | 2 defects/Hour | 0.6875
Requirement
Write requirements | 177 Req | 6.5 Req/Hour | 3.4 | 215 Req | 5 Req/Hour | 301 Req | 8 Req/Hour
Review Requirements
Preparation for review |  | 12.5 Req/Hour | 1.77 |  | 20 Req/Hour |  | 5 Req/Hour
Review Meeting |  | 9.5 Req/Hour | 2.33 |  | 11 Req/Hour |  | 8 Req/Hour
Rework | 90 defects | 8 defects/Hour | 1.41 | 120 defects | 5 defects/Hour | 137 defects | 10 defects/Hour
Build the development and testing lab environment
Hardware Environment
Servers | 10 | 1 server/day | 10
Clients | 28 | 5 clients/day | 5.6
Software Development Tools
Build/compile tools | 10 | 1 tool/Hour | 1.25
Software Testing Tools
Test Cases Execution tools | 12 | 1 tool/day | 12
Simulation tools | 5 | 1 tool/day | 5
Analysis
Write Analysis Document | 72 pages | 5 pages/Hour | 1.8 | 110 pages | 5 pages/Hour
Review Analysis Document
Preparation for Analysis Document |  | 5 pages/Hour | 1.8 |  | 5 pages/Hour
Review Meeting |  | 10 pages/Hour | 0.9 |  | 10 pages/Hour
Rework | 52 defects | 7 defects/Hour | 0.93 | 79 defects | 7 defects/Hour
Design
Write DD | 76 pages | 3.5 pages/Hour | 2.71 | 110 pages | 2 pages/Hour | 119 pages | 5 pages/Hour
Review DD
Preparation for DD |  | 5 pages/Hour | 1.9 |  | 5 pages/Hour |  | 5 pages/Hour
Review Meeting |  | 10 pages/Hour | 0.95 |  | 10 pages/Hour |  | 10 pages/Hour
Rework | 81 defects | 5 defects/Hour | 2.03 | 132 defects | 5 defects/Hour | 110 defects | 5 defects/Hour
Write Data Model (DM) | 36 pages | 0.75 pages/Hour |  | 50 pages | 0.5 page/Hours | 61 pages | 1 page/Hour
Review DM
Preparation for DM |  | 3 pages/Hour |  |  | 2 pages/Hour |  | 4 pages/Hour
Review Meeting |  | 7 pages/Hour |  |  | 6 pages/Hour |  | 8 pages/Hour
Rework | 70 defects | 4 defects/Hour |  | 141 defects | 4 defects/Hour | 66 defects | 4 defects/Hour
Coding
Write Code | 3000 SLOC | 5.5 SLOC/Hour | 68.18 | 5806 SLOC | 5 SLOC/Hour | 6391 SLOC | 6 SLOC/Hour
Unit Testing
Prepare/Execute Test Cases | 129 test cases | 8 Test Cases/Day | 16.125 | 210 test cases | 8 Test Cases/Day | 313 test cases | 1 Test Case/Hour
Fix Found Defects | 108 Defects | 5 Defects/Day | 21.6 | 180 Defects | 5 Defects/Day | 255 Defects | 5 Defects/Day
Test Fixed Defects | 108 Defects | 20 Defects/Day | 5.4 | 180 Defects | 31 Defects/Day | 255 Defects | 8 Defects/Day
Code Inspection
Preparation for Code Inspection |  | 110 SLOC/Hour | 3.41 |  | 100 SLOC/Hour |  | 120 SLOC/Hour
Code Inspection Meeting |  | 150 SLOC/Hour | 2.5 |  | 150 SLOC/Hour |  | 150 SLOC/Hour
Rework | 147 defects | 5 defects/Hour | 3.675 | 304 defects | 4 defects/Hour | 296 defects | 5 defects/Hour
Testing
Write test plan (TP) | 112 pages | 10 pages/Day | 11.2
Review TP
Preparation for TP |  | 4 pages/Hour | 3.5
Review TP Meeting |  | 10 pages/Hour | 1.4
Rework | 70 defects | 3 defects/Hour | 2.92
Execute TP (test cases) | 311 test cases | 19 test cases/day | 16.37
Fix Found Defects | 90 defects | 10 defects/day | 9
Test Fixed Defects | 90 defects | 15 defects/day | 6
Documentation
User Documentation | 231 pages | 4 page/Hour | 7.22 | 301 pages | 3 page/Hour | 247 pages | 5 page/Hour
Review UD
Preparation for UD Review |  | 6 pages/Hour | 4.81 |  | 7 pages/Hour |  | 5 pages/Hour
Review UD Meeting |  | 9 pages/Hour | 3.21 |  | 10 pages/Hour |  | 8 pages/Hour
Rework | 79 defects | 6 defects/Hour | 1.65 | 113 defects | 7 defects/Hour | 71 defects | 4 defects/Hour

## Sheet2
Task Name | Work | Duration | Early Start | Early Finish | Late Start | Late Finish | Start | Finish | Predecessors | Resource Names
Summary | 3,133.52 hrs | 86.4 days | Mon 4/4/16 | Tue 8/2/16 | Mon 4/4/16 | Tue 8/2/16 | Mon 4/4/16 | Tue 8/2/16
Project Plan | 192.48 hrs | 8.82 days | Mon 4/4/16 | Thu 4/14/16 | Mon 4/4/16 | Thu 4/14/16 | Mon 4/4/16 | Thu 4/14/16
Write Plan | 38 hrs | 4.75 days | Mon 4/4/16 | Fri 4/8/16 | Mon 4/4/16 | Fri 4/8/16 | Mon 4/4/16 | Fri 4/8/16 |  | PM9
Review Plan | 149.68 hrs | 3.47 days | Fri 4/8/16 | Thu 4/14/16 | Fri 4/8/16 | Thu 4/14/16 | Fri 4/8/16 | Thu 4/14/16 | 3
Preparation for review | 84.4 hrs | 2.11 days | Fri 4/8/16 | Tue 4/12/16 | Fri 4/8/16 | Tue 4/12/16 | Fri 4/8/16 | Tue 4/12/16 | 3 | SE74108,TE73812,DE45,RE76,PE6017
Review Meeting | 65.28 hrs | 1.36 days | Tue 4/12/16 | Thu 4/14/16 | Tue 4/12/16 | Thu 4/14/16 | Tue 4/12/16 | Thu 4/14/16 | 5 | PE6017,PM9,RE76,SE74108,TE73812,DE45
Rework | 4.8 hrs | 0.6 days | Thu 4/14/16 | Thu 4/14/16 | Thu 4/14/16 | Thu 4/14/16 | Thu 4/14/16 | Thu 4/14/16 | 6 | PM9
Documented Software Development Process Updates | 116.88 hrs | 4.72 days | Thu 4/14/16 | Thu 4/21/16 | Thu 4/14/16 | Thu 4/21/16 | Thu 4/14/16 | Thu 4/21/16 | 7
Process Changes | 8.8 hrs | 1.1 days | Thu 4/14/16 | Fri 4/15/16 | Thu 4/14/16 | Fri 4/15/16 | Thu 4/14/16 | Fri 4/15/16 | 7 | SE74108
Review Changes | 102.57 hrs | 2.93 days | Fri 4/15/16 | Wed 4/20/16 | Fri 4/15/16 | Wed 4/20/16 | Fri 4/15/16 | Wed 4/20/16 | 9
Preparation for review | 58.57 hrs | 1.83 days | Fri 4/15/16 | Tue 4/19/16 | Fri 4/15/16 | Tue 4/19/16 | Fri 4/15/16 | Tue 4/19/16 | 9 | DE45,PE6017,SE74107,TE73812
Review Meeting | 44 hrs | 1.1 days | Tue 4/19/16 | Wed 4/20/16 | Tue 4/19/16 | Wed 4/20/16 | Tue 4/19/16 | Wed 4/20/16 | 11 | DE45,PE6017,SE74107,SE74108,TE73812
Rework | 5.52 hrs | 0.69 days | Wed 4/20/16 | Thu 4/21/16 | Wed 4/20/16 | Thu 4/21/16 | Wed 4/20/16 | Thu 4/21/16 | 12 | SE74108
Requirement | 188.32 hrs | 7.21 days | Thu 4/21/16 | Mon 5/2/16 | Thu 4/21/16 | Mon 5/2/16 | Thu 4/21/16 | Mon 5/2/16 | 13
Write requirements | 27.2 hrs | 1.7 days | Thu 4/21/16 | Mon 4/25/16 | Thu 4/21/16 | Mon 4/25/16 | Thu 4/21/16 | Mon 4/25/16 | 13 | RE76,RE12
Review Requirements | 149.83 hrs | 4.1 days | Mon 4/25/16 | Fri 4/29/16 | Mon 4/25/16 | Fri 4/29/16 | Mon 4/25/16 | Fri 4/29/16 | 15
Preparation for review | 56.63 hrs | 1.77 days | Mon 4/25/16 | Wed 4/27/16 | Mon 4/25/16 | Wed 4/27/16 | Mon 4/25/16 | Wed 4/27/16 | 15 | DE45,PE6017,SE74108,TE73812
Review Meeting | 93.2 hrs | 2.33 days | Wed 4/27/16 | Fri 4/29/16 | Wed 4/27/16 | Fri 4/29/16 | Wed 4/27/16 | Fri 4/29/16 | 17 | DE45,PE6017,RE76,SE74108,TE73812
Rework | 11.28 hrs | 1.41 days | Fri 4/29/16 | Mon 5/2/16 | Fri 4/29/16 | Mon 5/2/16 | Fri 4/29/16 | Mon 5/2/16 | 18 | RE76
Build the development and testing lab environment | 270.8 hrs | 13.7 days | Thu 4/14/16 | Wed 5/4/16 | Wed 4/20/16 | Tue 5/10/16 | Thu 4/14/16 | Wed 5/4/16 | 7
Hardware Environment | 124.8 hrs | 5.2 days | Thu 4/14/16 | Fri 4/22/16 | Wed 4/20/16 | Wed 4/27/16 | Thu 4/14/16 | Fri 4/22/16 | 7
Servers | 80 hrs | 3.33 days | Thu 4/14/16 | Wed 4/20/16 | Wed 4/20/16 | Mon 4/25/16 | Thu 4/14/16 | Wed 4/20/16 | 7 | SE6,SE7,SE8
Clients | 44.8 hrs | 1.87 days | Wed 4/20/16 | Fri 4/22/16 | Mon 4/25/16 | Wed 4/27/16 | Wed 4/20/16 | Fri 4/22/16 | 22 | SE6,SE7,SE8
Software Development Tools | 10 hrs | 1.25 days | Fri 4/22/16 | Mon 4/25/16 | Fri 5/6/16 | Tue 5/10/16 | Fri 4/22/16 | Mon 4/25/16 | 23
Build/compile tools | 10 hrs | 1.25 days | Fri 4/22/16 | Mon 4/25/16 | Fri 5/6/16 | Tue 5/10/16 | Fri 4/22/16 | Mon 4/25/16 | 23 | SE6
Software Testing Tools | 136 hrs | 8.5 days | Fri 4/22/16 | Wed 5/4/16 | Wed 4/27/16 | Tue 5/10/16 | Fri 4/22/16 | Wed 5/4/16 | 23
Test Cases Execution tools | 96 hrs | 6 days | Fri 4/22/16 | Mon 5/2/16 | Wed 4/27/16 | Thu 5/5/16 | Fri 4/22/16 | Mon 5/2/16 | 23 | SE7,SE74107
Simulation tools | 40 hrs | 2.5 days | Mon 5/2/16 | Wed 5/4/16 | Thu 5/5/16 | Tue 5/10/16 | Mon 5/2/16 | Wed 5/4/16 | 27 | SE7,SE74107
Analysis | 115.43 hrs | 5.43 days | Mon 5/2/16 | Tue 5/10/16 | Mon 5/2/16 | Tue 5/10/16 | Mon 5/2/16 | Tue 5/10/16 | 19
Write Analysis Document | 14.4 hrs | 1.8 days | Mon 5/2/16 | Wed 5/4/16 | Mon 5/2/16 | Wed 5/4/16 | Mon 5/2/16 | Wed 5/4/16 | 19 | SE74108
Review Analysis Document | 93.6 hrs | 2.7 days | Wed 5/4/16 | Mon 5/9/16 | Wed 5/4/16 | Mon 5/9/16 | Wed 5/4/16 | Mon 5/9/16 | 30
Preparation for Analysis Document | 57.6 hrs | 1.8 days | Wed 5/4/16 | Fri 5/6/16 | Wed 5/4/16 | Fri 5/6/16 | Wed 5/4/16 | Fri 5/6/16 | 30 | PE6017,PE216,RE215,RE214
Review Meeting | 36 hrs | 0.9 days | Fri 5/6/16 | Mon 5/9/16 | Fri 5/6/16 | Mon 5/9/16 | Fri 5/6/16 | Mon 5/9/16 | 32 | PE216,PE6017,RE214,RE215,SE74108
Rework | 7.43 hrs | 0.93 days | Mon 5/9/16 | Tue 5/10/16 | Mon 5/9/16 | Tue 5/10/16 | Mon 5/9/16 | Tue 5/10/16 | 33 | SE74108
Design | 253.2 hrs | 13.74 days | Tue 5/10/16 | Fri 5/27/16 | Tue 5/10/16 | Fri 5/27/16 | Tue 5/10/16 | Fri 5/27/16 | 28,34,25
Write DD | 21.68 hrs | 2.71 days | Tue 5/10/16 | Thu 5/12/16 | Tue 5/10/16 | Thu 5/12/16 | Tue 5/10/16 | Thu 5/12/16 | 28,34,25 | SE74108
Review DD | 98.8 hrs | 2.85 days | Thu 5/12/16 | Tue 5/17/16 | Thu 5/12/16 | Tue 5/17/16 | Thu 5/12/16 | Tue 5/17/16 | 36
Preparation for DD | 60.8 hrs | 1.9 days | Thu 5/12/16 | Mon 5/16/16 | Thu 5/12/16 | Mon 5/16/16 | Thu 5/12/16 | Mon 5/16/16 | 36 | PE6017,PE216,SE74107,SE7
Review Meeting | 38 hrs | 0.95 days | Mon 5/16/16 | Tue 5/17/16 | Mon 5/16/16 | Tue 5/17/16 | Mon 5/16/16 | Tue 5/17/16 | 38 | PE216,PE6017,SE7,SE74107,SE74108
Rework | 11.2 hrs | 1.4 days | Tue 5/17/16 | Thu 5/19/16 | Tue 5/17/16 | Thu 5/19/16 | Tue 5/17/16 | Thu 5/19/16 | 39 | SE74108
Write Data Model (DM) | 48 hrs | 3 days | Thu 5/19/16 | Tue 5/24/16 | Thu 5/19/16 | Tue 5/24/16 | Thu 5/19/16 | Tue 5/24/16 | 40 | SE74108,SE74107
Review DM | 56 hrs | 1.59 days | Tue 5/24/16 | Wed 5/25/16 | Tue 5/24/16 | Wed 5/25/16 | Tue 5/24/16 | Wed 5/25/16 | 41
Preparation for DM | 30.4 hrs | 0.95 days | Tue 5/24/16 | Wed 5/25/16 | Tue 5/24/16 | Wed 5/25/16 | Tue 5/24/16 | Wed 5/25/16 | 41 | PE216,PE6017,SE6,SE7
Review Meeting | 25.6 hrs | 0.64 days | Wed 5/25/16 | Wed 5/25/16 | Wed 5/25/16 | Wed 5/25/16 | Wed 5/25/16 | Wed 5/25/16 | 43 | PE216,PE6017,SE6,SE7,SE74107
Rework | 17.52 hrs | 2.19 days | Wed 5/25/16 | Fri 5/27/16 | Wed 5/25/16 | Fri 5/27/16 | Wed 5/25/16 | Fri 5/27/16 | 44 | SE74107
Coding | 1,129.03 hrs | 36.03 days | Fri 5/27/16 | Mon 7/18/16 | Fri 5/27/16 | Mon 7/18/16 | Fri 5/27/16 | Mon 7/18/16 | 45
Write Code | 545.43 hrs | 17.04 days | Fri 5/27/16 | Tue 6/21/16 | Fri 5/27/16 | Tue 6/21/16 | Fri 5/27/16 | Tue 6/21/16 | 45 | PE6017,PE28,PE29,PE27
Unit Testing | 345.03 hrs | 11.23 days | Tue 6/21/16 | Thu 7/7/16 | Tue 6/21/16 | Thu 7/7/16 | Tue 6/21/16 | Thu 7/7/16 | 47
Prepare/Execute Test Cases | 129.03 hrs | 4.03 days | Tue 6/21/16 | Mon 6/27/16 | Tue 6/21/16 | Mon 6/27/16 | Tue 6/21/16 | Mon 6/27/16 | 47 | PE6017,PE27,PE28,PE29
Fix Found Defects | 172.8 hrs | 5.4 days | Mon 6/27/16 | Tue 7/5/16 | Mon 6/27/16 | Tue 7/5/16 | Mon 6/27/16 | Tue 7/5/16 | 49 | PE6017,PE27,PE28,PE29
Test Fixed Defects | 43.2 hrs | 1.8 days | Tue 7/5/16 | Thu 7/7/16 | Tue 7/5/16 | Thu 7/7/16 | Tue 7/5/16 | Thu 7/7/16 | 50 | PE6017,PE27,PE28
Code Inspection | 238.57 hrs | 7.75 days | Thu 7/7/16 | Mon 7/18/16 | Thu 7/7/16 | Mon 7/18/16 | Thu 7/7/16 | Mon 7/18/16 | 51
Preparation for Code Inspection | 109.12 hrs | 3.41 days | Thu 7/7/16 | Tue 7/12/16 | Thu 7/7/16 | Tue 7/12/16 | Thu 7/7/16 | Tue 7/12/16 | 51 | SE74107,SE74108,PE25,PE26
Code Inspection Meeting | 100 hrs | 2.5 days | Tue 7/12/16 | Fri 7/15/16 | Tue 7/12/16 | Fri 7/15/16 | Tue 7/12/16 | Fri 7/15/16 | 53 | PE25,PE26,PE6017,SE74107,SE74108
Rework | 29.43 hrs | 1.84 days | Fri 7/15/16 | Mon 7/18/16 | Fri 7/15/16 | Mon 7/18/16 | Fri 7/15/16 | Mon 7/18/16 | 54 | PE6017,PE27
Testing | 514.08 hrs | 65.65 days | Mon 5/2/16 | Tue 8/2/16 | Thu 6/30/16 | Tue 8/2/16 | Mon 5/2/16 | Tue 8/2/16 | 19
Write test plan (TP) | 89.6 hrs | 5.6 days | Mon 5/2/16 | Tue 5/10/16 | Thu 6/30/16 | Fri 7/8/16 | Mon 5/2/16 | Tue 5/10/16 | 19 | TE73812,TE3811
Review TP | 173.52 hrs | 6.51 days | Tue 5/10/16 | Wed 5/18/16 | Fri 7/8/16 | Mon 7/18/16 | Tue 5/10/16 | Wed 5/18/16 | 57
Preparation for TP | 112 hrs | 3.5 days | Tue 5/10/16 | Fri 5/13/16 | Fri 7/8/16 | Wed 7/13/16 | Tue 5/10/16 | Fri 5/13/16 | 57 | TE191,TE192,RE215,PE26
Review TP Meeting | 46.8 hrs | 1.17 days | Fri 5/13/16 | Tue 5/17/16 | Wed 7/13/16 | Fri 7/15/16 | Fri 5/13/16 | Tue 5/17/16 | 59 | PE26,RE215,TE191,TE192,TE3811
Rework | 14.72 hrs | 1.84 days | Tue 5/17/16 | Wed 5/18/16 | Fri 7/15/16 | Mon 7/18/16 | Tue 5/17/16 | Wed 5/18/16 | 60 | TE3811
Execute TP (test cases) | 130.97 hrs | 5.46 days | Mon 7/18/16 | Tue 7/26/16 | Mon 7/18/16 | Tue 7/26/16 | Mon 7/18/16 | Tue 7/26/16 | 61,55 | TE3811,TE73812,TE191
Fix Found Defects | 72 hrs | 3 days | Tue 7/26/16 | Fri 7/29/16 | Tue 7/26/16 | Fri 7/29/16 | Tue 7/26/16 | Fri 7/29/16 | 62 | PE6017,PE27,PE28
Test Fixed Defects | 48 hrs | 2 days | Fri 7/29/16 | Tue 8/2/16 | Fri 7/29/16 | Tue 8/2/16 | Fri 7/29/16 | Tue 8/2/16 | 63 | TE3811,TE73812,TE191
Documentation | 353.28 hrs | 65.65 days | Mon 5/2/16 | Tue 8/2/16 | Thu 7/14/16 | Tue 8/2/16 | Mon 5/2/16 | Tue 8/2/16 | 19
User Documentation | 57.77 hrs | 3.61 days | Mon 5/2/16 | Fri 5/6/16 | Thu 7/14/16 | Tue 7/19/16 | Mon 5/2/16 | Fri 5/6/16 | 19 | DE45,DE47
Review UD | 295.52 hrs | 62.04 days | Fri 5/6/16 | Tue 8/2/16 | Tue 7/19/16 | Tue 8/2/16 | Fri 5/6/16 | Tue 8/2/16 | 66
Preparation for UD Review | 153.92 hrs | 4.81 days | Fri 5/6/16 | Fri 5/13/16 | Tue 7/19/16 | Tue 7/26/16 | Fri 5/6/16 | Fri 5/13/16 | 66 | DE48,TE49,TE48,RE210
Review UD Meeting | 128.4 hrs | 3.21 days | Fri 5/13/16 | Wed 5/18/16 | Tue 7/26/16 | Fri 7/29/16 | Fri 5/13/16 | Wed 5/18/16 | 68 | DE45,DE48,RE210,TE48,TE49
Rework | 13.2 hrs | 1.65 days | Fri 7/29/16 | Tue 8/2/16 | Fri 7/29/16 | Tue 8/2/16 | Fri 7/29/16 | Tue 8/2/16 | 69,64FF | DE45