## Sheet1
Phase & tasks | work size | productivity | effort in days
project plan | 76 pages
write plan |  | 3pgs/hr | 3.16
Review plan
preparation |  | 5pgs/hr | 1.9
meeting |  | 8pgs/hr | 1.18
rework | 46 defects | 5 defects/hr | 1.15
Documented Software Development Process Updates
process changes | 44 changes | 5 changes/hr | 1.1
Review changes
preparation |  | 3 changes/hr | 1.83
meeting |  | 5 changes/hr | 1.1
rework | 11 defects | 2 defects/hr | 0.68
Requirement | 177 requests
write requirement |  | 5 requests/hr | 4.425
Review
preparation |  | 13 requests/hr | 1.7
meeting |  | 11 requests/hr | 2
rework | 91 defects | 8 defects/hr | 1.42
Build the development and testing lab environment
hardware environment
servers | 10 server | 1 servers/day | 10
clients | 28 clients | 5 clients/day | 5.6
Software development tools
build/compile tools | 10 tools | 1 tool/hr | 1.25
software testing tools
test cases execution tools | 12 tools | 1 tool/day | 12
simulation tools | 5 tools | 1 tool/day | 5
Analysis | 72 pages
Write analysis |  | 5 pgs /hr | 1.8
Review
preparation |  | 5 pgs/hr | 1.8
meeting |  | 10 pgs/hr | 0.9
rework | 57 defects | 6 defects/hr | 1.18
Design | 76 pages
Write design document |  | 4 pgs/hr | 2.37
Review
preparation |  | 5 pgs/hr | 1.9
meeting |  | 10 pgs/hr | 0.95
rework | 81 defects | 5 defects/hr | 2.02
Coding
Write Code | 4570 SLOC | 6 SLOC/Hour | 95.2
Unit Testing
Prepare/Execute Test Cases | 202 test cases | 1 Test Case/Hour | 25.25
Fix Found Defects | 170 Defects | 5 Defects/Day | 34
Test Fixed Defects | 170 Defects | 21 Defects/Day | 8
Code Inspection
Preparation for Code Inspection |  | 110 SLOC/Hour | 5.19
Code Inspection Meeting |  | 150 SLOC/Hour | 3.8
Rework | 293 defects | 5 defects/Hour | 7.32
Testing
Write test plan (TP) | 112 pages | 10 pages/Day | 11.2
Review TP
Preparation for TP |  | 4 pages/Hour | 3.5
Review TP Meeting |  | 10 pages/Hour | 1.4
Rework | 70 defects | 3 defects/Hour | 2.91
Execute TP (test cases) | 311 test cases | 19 test cases/day | 16.3
Fix Found Defects | 90 defects | 10 defects/day | 9
Test Fixed Defects | 90 defects | 15 defects/day | 6
Documentation | 231 pages
Write document |  | 5 pgs/hr | 5.77
Review
preparation |  | 6 pgs/hr | 4.8
meeting |  | 10 pgs/hr | 2.88
rework | 133 defects | 6 defects/hr | 2.77